## Sprint 4
Sprint start date: | 2019-11-22
Sprint end date: | 2019-12-05
Description | Magnitude | Finish Date | Complete | Total | Done | To Do
|  |  |  | 0 | 0 | 0

## Sprint 3
Sprint start date: | 2020-02-03
Sprint end date: | 2020-02-10
Description | Magnitude | Start Date | Finish Date | Complete | Total | Done | To Do
[5 empty] | 14 | 0 | 14
Raspberry Pi - Rust
Get / Set GPIO | 2
Hello World | 1
Road-map
Update version timelines | 1
Update 'done' | 2
Research - Rust
TCP socket | 2
Security (SSL or other) | 2
Review
Xamarin project | 1
Rust example notes | 2
TCP protocol | 1

## Sprint 2
Sprint start date: | 2019-01-06
Sprint end date: | 2019-01-12
Description | Magnitude | Finish Date | Complete | Total | Done | To Do
|  |  |  | 14 | 0 | 14
Raspberry Pi - Rust
Hello world | 1
Get / Set GPIO | 2
Road-map
Update version timelines | 1
Update 'done' | 2
Research - Rust
TCP socket | 2
Security (SSL or other) | 2
Review
Xamarin project | 1
Rust example notes | 2
TCP protocol | 1

## Sprint 1
Sprint start date: | 2019-11-22
Sprint end date: | 2019-12-05
Description | Magnitude | Finish Date | Complete | Total | Done | To Do
|  |  |  | 46 | 9 | 37
Server - Research (Rust)
Rust Doc Ch7 | 1 | 2019-11-24 | 1
Rust Doc Ch8 | 1 | 2019-11-25 | 1
Rust Doc Ch9 | 1
Rust Doc Ch10 | 1
Rust Doc Ch11 | 1
Rust Doc Ch12 | 1
Rust Doc Ch13 | 1
Rust Doc Ch14 | 1
Rust Doc Ch15 | 1
Rust Doc Ch16 | 1
Rust Doc Ch17 | 1
Rust Doc Ch18 | 1
Rust Doc Ch19 | 1
Rust Doc Ch20 | 1
Mobile - UI mock-up
LocksListView | 2
LockView | 2
PermissionsView | 2
AddView | 2
RemoveView | 2
RenameView | 2
SharedView | 2
ActionConfirmationPopups | 2
Hamburger drop-down | 1
Back arrow | 1
Mobile Architecture
Lock class | 1 | 2019-12-05 | 1
Permissions class | 2
IService interface | 1 | 2019-11-25 | 1
PrototypeService class | 1
IConnection interface | 1 | 2019-11-25 | 1
LANConnection stubbed class | 1 | 2019-11-25 | 1
Server - Architecture (stubbed)
Rust project | 1 | 2019-11-29 | 1
Input class | 2
Output class | 2
User class | 2 | 2019-11-29 | 2
Server - Command line
Parse 1st level commands | 2 | 2019-12-03 | 2
Usage function | 1 | 2019-12-03 | 1
Time Window class stub | 1 | 2019-12-04 | 1